## Sheet1
Context | Inputs |  | Planning | Outputs |  | Aims and Objectives | Outcomes Evaluation |  |  | Outcomes Evaluation |  |  | Outcomes Evaluation
| Praxis team | Resources |  | Activities | Participants |  | Short term benefits |  |  | Medium Term outcomes |  |  | Longer term impact
[7 empty] | Change | Indicators | Evaluation measures | Change | Indicators | Evaluation measures | Change | Indicators | Evaluation measures
What issue(s) do you want to address with your intervention? | Who needs to be involved in scoping, designing, planning, delivering and/or evaluating your intervention? Think about partners and stakeholders as well as staff. | What other resources - time, money, equipment, etc. - do you need to scope, design, plan, deliver and/or evaluate the intervention? | Why are you doing this particular intervention? What evidence do you have that it is needed? What evidence do you have that it will work? How will it work? | How will you address the issues identified? What is the intervention you are proposing? | Who or what are the targets for the intervention? Who needs to be engaged? | What are the main NERUPI / additional aims and objectives for the intervention? | Initial learning as part of the intervention | What specifically will you use as evidence of this change? What does success look like? Be precise. Be aware of your assumptions. | How will you gather the evidence? What methods will you use? | development of knowledge, skills, attitudes, processes, culture, etc. needed to move towards longer term impact | What specifically will you use as evidence of this change? What does success look like? Be precise. Be aware of your assumptions. | How will you gather the evidence? What methods will you use? | Significant change which addresses the issue(s) identified in the first column | What specifically will you use as evidence of this change? What does success look like? Be precise. Be aware of your assumptions. | How will you gather the evidence? What methods will you use?
|  |  |  | Output can be counted but can't determine effectiveness of intervention. EG: 10 workshops for 150 staff members |  | Use the NERUPI Framework mapping template for a full analysis of aims and objectives |  |  |  | There may be several medium term outcomes at different stages
EXAMPLE
Awarding gaps between black and white students | Curriculum and Pedagogy Director & others from Exec team & quality team. Staff development team. EDI reps. Faculty deans and heads of department. Course leaders. Student reps. Library and learning support reps. Colleagues with expertise from other institutions, for advice and as guest speakers. Assign senior academic as evaluation lead plus supporting team. | 18 months for workshops and development of new curricula in target departments - to be implemented and evaluated in following academic year. Significant budget commitment required for staff time & possible new or enhanced posts, for workshop delivery, for new materials, library and learning resources, etc. | Evidence of successful curriculum reviews at other institutions where has had a positive effect on reducing awarding gaps as well as improving students' sense of belonging. | Development of curriculum review process including drawing on experience of other institutions. | Educational development team; curriculum review working group; staff at other institutions. | NERUPI Level 5: Student Success | Academic staff who participate in workshops will gain: knowledge (about inclusive curricula, how to engage all students in the drive for inclusive curricula, how to do a successful review); | Participants able to accurately identify the key elements of an inclusive curriculum and best practice principles for conducting a curriculum review. | Participants will need to complete an online quiz within 2 days of workshop and achieve at least 90% score. | STAGE 1: Staff express support for inclusive curriculum initiatives. . | Staff engage in curriculum review process and are confident in applying skills and knowledge of curricula review. | Share of staff taking part across departments; relevant questions on staff survey; possible focus groups. | Awarding gap significantly narrower between black and white students on all courses reviewed and particularly in target departments. | gap in 1st and 2:1 degree outcomes between black and white students are at least 50% reduced for students on new curricula compared to old curricula. | Analysis of degree results data and comparison over time.
|  |  |  | Curriculum review process undertaken including series of staff development workshops. | Curricula and academic staff across institution. | NERUPI Aims: Become: Develop students' confidence and resilience to negotiate the challenge of university life | skills (in using tools to review own curricula and make inclusive for all students). | Participants will demonstrate ability to apply tools to review curriculum for inclusivity. | Curriculum review task during workshop - course teams will be observed during task and their completed curriculum review sheet assessed. | Students are successfully engaged in and support inclusive curriculum initatives. | Students engage in curriulum review process and feel this to be an inclusive experience. | Student rep and general student surveys; possible focus groups. | Inclusive curriculum principles and practice embedded in the institutional culture. | Inclusive curriculum principles are standard in course validation and review processes. | Critical analysis of course validation guides, templates and processes.
|  |  |  | Development and implementation of new curricula as needed. | Course curricula and management teams in particular departments where are significant awarding gaps between white and black students. |  |  |  |  | Successful curriculum reviews conducted by course teams Appropriate curriculum changes validated and resourced in time for start of academic year | Curriculum reviews completed. resource requiments identified for curriulum resources for curriulum changes put in place by September. | Records of curriculum review meetings, etc. in departments; record of resource requirements. |  | Staff and students strongly support and promote inclusive curriculum. | Focus groups, interviews and case studies with staff and students.
[6 empty] | Objectives: Enable students to maximise the benefits of university life and successfully progress to graduate employment |  |  |  | Appropriate curriculum changes focusing on inclusivity in target departments are successfully validated SEE NOTE BELOW IN YELLOW | Course validations agreed which focus on inclusive curriculum. | Curriculum validation paperwork 'marked' against inclusive practice checklist and amended as needed for final approval. |  | Staff and students from black and ethnic minority backgrounds feel represented in the curriculum. | Focus groups, interviews and case studies with staff and students.
Note: additional columns could be added fo subsequent medium term outcomes, eg:
Stage 2: New curricula delivered, especially in target departments, which are effective and inclusive for all students and which have a demonstrable impact on assessment gaps in Years 1 and 2.